## Dashboard
SPACE STATION AURORA - PROJECT CONTROL
Initial status is inferred from the existing files. Update statuses as work changes.
PROJECT STATE | WORKING CANON / PRE-ALPHA
Current focus | Lock story and puzzle dependencies before producing more props
Biggest blocker | Missing E.V.I.L. memo, incomplete H.A.R.O.L.D. progression, and unclued hardware settings
Next review | Decision Log -> P0 items -> first end-to-end paper prototype
Puzzle status | Count | Asset state | Count
BUILT | 1 | BUILT | 5
PARTIAL | 4 | PARTIAL | 4
PROPOSED | 3 | PLACEHOLDER | 2
TBD | 2 | CONCEPT | 4
P0 PRIORITIES
1 | Accept/revise canonical decisions |  | Decision Log | Prevents story contradictions
2 | Lock puzzle outputs and unlocks |  | Puzzle Register | Prevents disconnected props
3 | Write decisive E.V.I.L. memo |  | Asset Register | Creates proof, not just suspicion
4 | Implement five H.A.R.O.L.D. modules |  | Puzzle Register | Makes digital progression completable
5 | Create fair clues for control settings / 8536 |  | Puzzle Register | Makes hardware solvable
METHOD: status reflects evidence found in the folder, not confirmation that a physical component has been built or playtested.

## Puzzle Register
PUZZLE REGISTER
One row per puzzle. Every puzzle needs a fair input, method, unique output, feedback, and unlock.
ID | Act | Puzzle / beat | Player goal | Inputs | Interaction | Output / answer | Unlocks | Status | Evidence | Next action | Notes / risks
P00 | Setup | Mission briefing | Understand role and crisis | Briefing; Sarah ID; roster | Read and inventory | Mission understood | Damage-map puzzle | PARTIAL | Briefing and crew designs exist | Reconcile crew details | Do not expose sabotage yet
P01 | I | Damage map | Restore communications | Blueprint; corrupted damage data | Cross out / trace grid | ORBIT | H.A.R.O.L.D. comms | PROPOSED | ORBIT exists in website; map idea in deck | Design printable map and fair damage data | Current DXF is not a finished puzzle
P02 | I | Communications restore | Get instructions from H.A.R.O.L.D. | ORBIT | Enter code in terminal | Communications active | Crew anomaly clue | PARTIAL | ORBIT handler implemented | Add response, state persistence, duplicate protection | Only one module currently works
P03 | II | Crew anomaly | Understand why Alistair is aboard | Briefing; IDs; roster; allergy data | Compare records | Pascale was targeted | Receipt focus | PROPOSED | Required facts exist across drafts | Choose exact answer and validation | Control deliberate vs accidental inconsistencies
P04 | II | Allergen trail | Connect Alistair to Pascale's reaction | Pascale allergy; Fish and Nuts receipt | Match items and use receipt total | 2912 (proposed) | Evidence compartment A | PROPOSED | $29.12 receipt is designed | Confirm lock type and compartment | Never use real allergens
P05 | II | Financial trail | Identify motive and sponsor | Betting emails; bank statement | Trace losses and unusual deposit | EVIL | Corporate evidence path | BUILT | Printable emails and bank statement exist | Decide terminal answer vs word lock | Strong evidence but not yet decisive proof
P06 | III | Control panel A | Restore a station function | Control-settings clue TBD | SW1 ON; SW2 OFF; dials 80/20/60 | Servo 1 opens | Repair/evidence item | PARTIAL | Hardware settings and wiring documented | Create clue source and feedback | No player-facing derivation exists
P07 | III | Control panel B | Open specialized-tool compartment | Second settings clue TBD | SW1 OFF; SW2 ON; dials 20/80/40; keypad | 8536# | Servo 2 opens | PARTIAL | Sequence documented in Support_Excel | Create derivation for 8536 | Keypad answer currently appears only in design data
P08 | IV | Corporate proof | Prove deliberate sabotage | E.V.I.L. memo; bank evidence | Reconcile order, payment, and failure | Proof complete | Sabotage protocol | TBD | Memo file contains header only | Write decisive memo content | Must turn suspicion into proof
P09 | IV | Final transmission and repair | Expose plot and evacuate | Proof; special tool; final code TBD | Transmit evidence and perform repair | Mission complete | Ending | TBD | Finale described only at concept level | Design physical action and digital ending | Confirm both survival and evidence sent

## Asset Register
ASSET REGISTER
Tracks what exists, what job it performs, and what prevents it from being final.
Asset | Type | Player-facing? | Related puzzle | State | What exists | Gap / issue | Next action | Source path
Mission briefing | DOCX | Yes | P00 | BUILT | Designed one-page briefing | Canon and crew details need reconciliation | Revise after decisions are accepted | Text_Briefing_Note_Start.docx
Betting emails | DOCX | Yes | P05 | BUILT | Two pages of account correspondence | Minor sender/signature inconsistencies | Proofread and lock dates | Text_Betting_Emails.docx
E.V.I.L. memo | DOCX | Yes | P08 | PLACEHOLDER | Branded header only | No body or decisive proof | Write final memo | Text_Memo_Evil.docx
Bank statement | XLSX / print | Yes | P05 | BUILT | Formatted statement with losses and $1M credit | Chronology/order should be reviewed | Validate dates and totals | Support_Excel.xlsx / Bank_Statement
H.A.R.O.L.D. terminal | HTML | Yes | P02-P09 | PARTIAL | Responsive terminal; help; progress; one code | Only ORBIT works; repeated entry can advance count | Implement state machine for all modules | Website_Harold.html
Electronic control panel | Hardware design | Yes | P06-P07 | PARTIAL | Parts list, wiring, two configurations | Build/test state unknown; settings are unclued | Prototype and create clue derivations | Support_Excel.xlsx
Backpack compartment geometry | 3D design notes | No | P06-P07 | PARTIAL | Early size/volume calculations | No printable models found | Confirm mechanical design and files | Support_Excel.xlsx / 3DPrinting
Station blueprint | DXF / image | Yes | P01 | PLACEHOLDER | Basic DXF geometry and generic example image | No completed Aurora map puzzle | Redesign as explicit ORBIT puzzle | Station_BluePrint.dxf; Images/BluePrint_Example.png
Crew cards | PPTX / images | Yes | P00-P04 | PARTIAL | Multiple visual designs and core facts | Dates and hometowns conflict | Create one canonical crew data sheet | Support_Design.pptx; Images/
Receipt | PPTX design | Yes | P04 | BUILT | Fish and Nuts receipt totaling $29.12 | Lock mapping not yet confirmed | Export final print asset after decision | Support_Design.pptx
Corporate / world logos | Images | Yes | Multiple | BUILT | Aurora, MAPLE, EVIL, bank, betting, shop, HAROLD | Some styles vary | Select final variants and archive extras | Images/
QR / welcome card | PPTX design | Yes | P02 | CONCEPT | Welcome-card concept with QR | Destination and role are not documented | Define link, backup URL, and offline plan | Support_Design.pptx
Solution guide | Document | No | All | CONCEPT | No final walkthrough found | Cannot facilitate or reset consistently | Create after puzzle flow is locked | Not yet created
Hint ladder | Digital / document | Yes | All | CONCEPT | Generic website help only | No puzzle-specific hints | Write three hints per puzzle | Not yet created
Reset / packing guide | Checklist | No | All | CONCEPT | No reset document found | Operational risk between groups | Create inventory and reset sequence | Not yet created

## Decision Log
DECISION LOG
Accept, reject, or revise these before treating the Adventure Bible as final canon.
ID | Topic | Proposed decision | Why | Status | Decision date | Impact if changed | Notes
D01 | Player role | Player is Dr. Sarah Lancaster, biologist/physician | Matches the clearest story draft | PROPOSED |  | Briefing, IDs, website copy
D02 | Incident causality | Micrometeorite strike is genuine; sabotage amplified the damage | Unifies accident and conspiracy | PROPOSED |  | Story, memo, finale
D03 | Antagonist | Alistair is a planted replacement engineer using a controlled identity | Explains conflicting origin data and access | PROPOSED |  | Crew cards, proof chain
D04 | Pascale | Alistair deliberately exposed Pascale to peanuts/shellfish before launch | Connects briefing, allergy, and receipt | PROPOSED |  | Briefing, receipt, memo
D05 | Corporate motive | E.V.I.L. wants Aurora decommissioned so it can win the replacement contract | Matches concept deck | PROPOSED |  | Memo and ending
D06 | Receipt code | Use 2912 as the four-digit output | Uses an existing, visible receipt total | NEEDS DECISION |  | Physical lock choice | Could instead be evidence only
D07 | Alistair identity data | Red Deer is the claimed hometown; Waco is the discovered truth | Turns inconsistency into a controlled clue | NEEDS DECISION |  | Crew records and bank statement
D08 | Active cast | Keep Sarah, Helena, Alistair, and Pascale as the core named cast | Reduces cognitive load | PROPOSED |  | Crew assets | Other names can remain background
D09 | Final success | Mission succeeds only when systems are repaired and sabotage evidence is sent | Pays off both halves of the adventure | PROPOSED |  | Website and final compartment

## Playtest Log
PLAYTEST LOG
Add one row per group. Record observed behavior, not only whether they escaped.
Date | Build | Group | Players | Completed? | Stop point | Elapsed time | Hints used | Puzzle failures | Tech failures | What confused players | What delighted players | Actions | Retest?

## Idea Backlog
IDEA BACKLOG
Capture ideas here without disrupting the accepted puzzle flow. Promote only after a decision.
ID | Idea | Category | Expected benefit | Complexity | Priority | Status | Decision / notes
I01 | H.A.R.O.L.D. messages become progressively less scrambled as modules return | Digital | Visible restoration progress | Medium | P1 | KEEP | Already aligned with concept deck
I02 | Use damaged station modules on a grid to produce ORBIT | Puzzle | Makes the blueprint mechanically relevant | Medium | P0 | EVALUATE | Needs a fair, testable extraction
I03 | Reveal Alistair's Waco address only in the bank statement | Story | Supports false-identity reveal | Low | P1 | EVALUATE | Depends on D07
I04 | Allow financial and allergy evidence branches to be solved in parallel | Flow | Reduces idle time for groups | Low | P1 | KEEP | Both branches must merge before finale
I05 | Use distinct sound/light feedback for each restored system | Hardware | Clear feedback and atmosphere | Medium | P2 | BACKLOG | Provide silent accessibility equivalent
I06 | Include a printed backup URL/code beneath every QR | Reliability | Prevents camera/network dead ends | Low | P1 | KEEP | Required for portable play
I07 | Final tool physically opens the evidence panel | Finale | Strong tactile payoff | High | P1 | EVALUATE | Needs safe, repeatable mechanism
I08 | Create optional role cards for multi-player groups | Replayability | Improves teamwork | Medium | P2 | BACKLOG | Do not expand core cast unless needed